## ProjectSchedule
QUẢN LÝ SIÊU THỊ
|  | Ngày bắt đầu đồ án: | 2020-10-26
|  | Hôm nay: | 2020-11-21
|  | Hiển thị tuần: | 1 |  |  | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14
 | time axis 2020-10-26 to 2020-12-20
Công việc | Phân công | Tiến độ | Ngày bắt đầu | Ngày kết thúc | DAYS | time axis 2020-10-26 to 2020-12-20
Giai đoạn 1: Phân tích
Danh sách Biểu mẫu, Quy định | Mụi | 100% | 2020-10-26 | 2020-11-01 | 7
Lập bảng yêu cầu, trách nhiệm nghiệp vụ | Trường | 100% | 2020-10-26 | 2020-11-01 | 7
Lập bảng yêu cầu, trách nhiệm tiến hóa | Tuấn | 100% | 2020-10-26 | 2020-11-01 | 7
Lập bảng yêu cầu, trách nhiệm hiệu quả | Khôi | 100% | 2020-10-26 | 2020-11-01 | 7
Lập bảng yêu cầu, trách nhiệm bảo mật | Huy | 100% | 2020-10-26 | 2020-11-01
Lập bảng yêu cầu, trách nhiệm công nghệ | Khoa | 100% | 2020-10-26 | 2020-11-01
Lập bảng yêu cầu, trách nhiệm tiện dụng | Duy | 100% | 2020-10-26 | 2020-11-01
Lập bảng yêu cầu, trách nhiệm tương thích | Kỷ | 100% | 2020-10-26 | 2020-11-01 | 7
Giai đoạn 2: Thiết kế DFD
Vẽ DFD Mức 0 | Trường | 100% | 2020-11-02 | 2020-11-04 | 3
Vẽ DFD Mức 1 của chức năng tiếp nhận hồ sơ nhân viên | Tuấn | 100% | 2020-11-04 | 2020-11-06 | 3
Vẽ DFD Mức 1 của chức năng quản lý ca làm nhân viên | Khoa | 100% | 2020-11-04 | 2020-11-06 | 3
Vẽ DFD Mức 1 của chức năng cấp tài khoản nhân viên | Duy | 100% | 2020-11-04 | 2020-11-06 | 3
Vẽ DFD Mức 1 của chức năng quản lý chức vụ | Kỷ | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng tiếp nhận khách hàng | Kỷ | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng quản lý tủ đồ | Triều | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng quản lý sản phẩm | Khôi | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng kiểm kê sản phẩm lỗi | Duy | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng phân loại hàng theo danh mục | Trường | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng giữ trả xe | Huy | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng quản lý nhà cung cấp | Trường | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng kiểm kê hàng tồn kho | Khôi | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng quản lý phiếu nhập | Mụi | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng lập phiếu xuất | Mụi | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng lập hóa đơn | Huy | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng tổ chức khuyến mãi | Khoa | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng thống kê doanh thu | Triều | 100% | 2020-11-04 | 2020-11-06
Vẽ DFD Mức 1 của chức năng thống kê lợi nhuận | Tuấn | 100% | 2020-11-04 | 2020-11-06 | 3
Giai đoạn 3: Thiết kế ERD
Vẽ ERD | Huy | 100% | 2020-11-06 | 2020-11-08 | 3
Giai đoạn 4: Lập các bảng thiết kế phần mềm
Thiết kế giao diện chức năng |  | 100% | 2020-11-09 | 2020-11-18 | 10
Thiết kế giao diện chức năng |  | 100% | 2020-11-09 | 2020-11-18 | 10
Thiết kế giao diện chức năng |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế dữ liệu bảng |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế dữ liệu bảng |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế dữ liệu bảng |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế xử lý |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế xử lý |  | 100% | 2020-11-09 | 2020-11-18
Thiết kế xử lý |  | 100% | 2020-11-09 | 2020-11-18 | 10
Giai đoạn 5: Thiết kế Sequence Diagram
Task 1 |  | 0% | 2020-11-19 | 2020-11-24 | 6
Task 2 |  | 0% | 2020-11-19 | 2020-11-24 | 6
Task 3 |  | 0% | 2020-11-19 | 2020-11-24 | 6
Task 4 |  | 0% | 2020-11-19 | 2020-11-24 | 6
Task 5 |  | 0% | 2020-11-19 | 2020-11-24 | 6
Giai đoạn 6: Thiết kế Activity Diagram
Task 1 |  |  | 2019-02-05 | 2019-02-10 | 6
Giai đoạn 7: Thiết kế State Machine Diagram
Task 1 |  |  | 2019-02-05 | 2019-02-10 | 6
Giai đoạn 8: Thiết kế Usecase
Task 1 |  |  | 2019-02-05 | 2019-02-10 | 6
Insert new rows ABOVE this one
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.